{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["开发计划清单","模块概览","API 接口清单","里程碑节点"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"开发计划清单","index":0,"n_rows":44,"n_cols":12,"rows_kept":44,"cut":false,"hidden":false,"merged":[[0,0,0,11],[1,0,1,11]]}
["盈科开放平台 - 开发计划清单"]
["时间周期：2026 年 4 月 7 日 - 2026 年 4 月 24 日（共 14 个工作日）"]
[]
["优先级","模块名称","任务 ID","任务名称","任务描述","API 接口","前端组件","工期（天）","开始日期","结束日期","完成标准","状态"]
["P0，应用广场，APP-001，应用列表展示，展示应用卡片列表，支持分页，GET /bigmodel/api/getApplicationList","AppPlazaList.tsx","0.5","4/7","4/7，列表正常渲染分页可用，待开发"]
["P0，应用广场，APP-002，应用卡片组件，应用卡片 UI 包含图标名称描述标签等，-","AppCard.tsx","0.5","4/7","4/8","UI 还原设计稿，待开发"]
["P0，应用广场，APP-003，筛选功能，支持按分类状态关键词筛选，POST /bigmodel/api/getApplicationList (params)","FilterBar.tsx、FilterDrawer.tsx","0.5","4/8","4/8，筛选条件生效，待开发"]
["P0，应用广场，APP-004，排序功能，综合排序最新上线高频率调用，前端排序，排序按钮组件，0.5","4/8","4/9，排序逻辑正确，待开发"]
["P0，应用广场，APP-005，应用详情，点击卡片查看详情，GET /bigmodel/api/selectApplication/:id","AppDetailModal.tsx","0.5","4/9","4/9，详情数据完整，待开发"]
["P0，应用广场，APP-006，立即体验，跳转至智能问答界面，-","跳转逻辑，0.25","4/9","4/9，跳转正常，待开发"]
["P0，应用广场，APP-007","API 调用入口，查看 API 文档获取调用凭证，GET /bigmodel/api/getAppApiKey","ApiDocModal.tsx","0.25","4/9","4/9，弹窗展示 API 信息，待开发"]
["P0，应用广场，APP-008，联调测试，与后端联调验证数据交互，全部应用相关接口，-","0.5","4/9","4/9，接口对接完成，待开发"]
["P0","API 接口，API-001","API 密钥管理列表，展示 API Key 列表支持创建删除，GET /bigmodel/api/apiKey/list","ApiKeyList.tsx","0.5","4/10","4/10，列表展示完整，待开发"]
["P0","API 接口，API-002，创建 API Key，弹窗创建新的 API Key","POST /bigmodel/api/apiKey/create","ApiKeyModal.tsx","0.5","4/10","4/11，创建成功并展示 Key，待开发"]
["P0","API 接口，API-003，删除 API Key，删除 API Key 确认弹窗，DELETE /bigmodel/api/apiKey/delete，确认弹窗，0.25","4/11","4/11，删除成功，待开发"]
["P0","API 接口，API-004","API 调用统计，展示各应用调用次数图表，GET /bigmodel/api/apiKey/stats","G2Plot 图表，0.5","4/11","4/11，图表渲染正确，待开发"]
["P0","API 接口，API-005，接口文档页面，展示 RAG 调用接口文档，-","ApiDocPage.tsx","0.25","4/11","4/11，文档页面完成，待开发"]
["P0，知识库，KB-001，知识库列表，展示知识库列表支持分页，POST /bigmodel/api/knowledgeList","KnowledgeLibList.tsx","0.5","4/14","4/14，列表正常渲染，待开发"]
["P0，知识库，KB-002，创建知识库，弹窗创建知识库，POST /bigmodel/api/createKnowledge","InfoModal.tsx","0.5","4/14","4/15，创建成功，待开发"]
["P0，知识库，KB-003，编辑知识库，修改知识库信息，PUT /bigmodel/api/updateKnowledge","InfoModal.tsx","0.25","4/15","4/15，更新成功，待开发"]
["P0，知识库，KB-004，删除知识库，删除知识库含确认，DELETE /bigmodel/api/delKnowledge，确认弹窗，0.25","4/15","4/15，删除成功，待开发"]
["P0，知识库，KB-005，知识库详情，进入知识库详情页，GET /bigmodel/api/detailKnowledge/:id","KnowledgeDetail.tsx","0.5","4/15","4/16，详情数据完整，待开发"]
["P0，知识库，KB-006，文档管理，文档列表上传删除，POST /bigmodel/api/documentList 等，DocumentList.tsx","0.5","4/16","4/16，文档操作完整，待开发"]
["P0，知识库，KB-007，切片管理，查看和编辑文档切片，POST /bigmodel/api/getSliceList","SliceList.tsx","0.5","4/16","4/16，切片展示正确，待开发"]
["P0，知识库，KB-008，修订工具，切片修订历史与对比，GET /deepseek/revise/pageList","RevisionTool.tsx","0.5","4/16","4/16，修订功能可用，待开发"]
["P0，知识库，KB-009，联调测试，与后端联调知识库接口，全部知识库接口，-","0.5","4/16","4/16，接口对接完成，待开发"]
["P1，我创建的应用，MYAPP-001，我的应用列表，展示当前用户创建的应用，GET /bigmodel/api/myApplications","MyApplicationsList.tsx","0.5","4/17","4/17，列表渲染正确，待开发"]
["P1，我创建的应用，MYAPP-002，应用状态筛选，全部/已上线/已下线/审核中，前端筛选，Tabs 组件，0.25","4/17","4/18，筛选生效，待开发"]
["P1，我创建的应用，MYAPP-003，编辑应用，修改应用配置，PUT /bigmodel/api/updateApplication/:id","AppEditForm.tsx","0.5","4/17","4/18，更新成功，待开发"]
["P1，我创建的应用，MYAPP-004，应用数据统计，调用次数用户数等统计，GET /bigmodel/api/app/stats","StatsPanel.tsx","0.5","4/18","4/18，统计数据正确，待开发"]
["P1，我创建的应用，MYAPP-005，应用下线/上线，切换应用状态，PUT /bigmodel/api/updateApplication/status，状态切换按钮，0.25","4/18","4/18，状态切换成功，待开发"]
["P1，智能问答系统，CHAT-001，应用跳转问答，从应用广场跳转到问答系统，-","跳转逻辑，0.25","4/21","4/21，携带 appId 跳转，待开发"]
["P1，智能问答系统，CHAT-002，问答接口对接，RAG 检索 + 大模型回答，POST /bigmodel/api/chat/stream","ChatInterface.tsx","1","4/21","4/22，流式响应正常，待开发"]
["P1，智能问答系统，CHAT-003，历史记录同步，获取和展示聊天历史，POST /bigmodel/api/chatHistory/list","HistoryList.tsx","0.5","4/22","4/22，历史记录完整，待开发"]
["P1，智能问答系统，CHAT-004，跨系统通信，两个系统间用户态同步，-","通信逻辑，0.25","4/22","4/22，用户态一致，待开发"]
["P2，应用审核，AUDIT-001，审核列表，展示待审核/已通过/已拒绝应用，GET /bigmodel/api/audit/list","AuditList.tsx","0.3","4/23","4/23，列表渲染正确，待开发"]
["P2，应用审核，AUDIT-002，审核通过，审核通过操作，POST /bigmodel/api/audit/approve，审核弹窗，0.2","4/23","4/23，审核成功，待开发"]
["P2，应用审核，AUDIT-003，审核拒绝，审核拒绝操作，POST /bigmodel/api/audit/reject，审核弹窗，0.2","4/23","4/23，拒绝成功，待开发"]
["P2，应用审核，AUDIT-004，应用详情预览，查看应用详情及知识库，GET /bigmodel/api/audit/detail/:id","AuditDetailDrawer.tsx","0.2","4/23","4/23，详情完整，待开发"]
["P2，应用审核，AUDIT-005，审核统计，待审核/通过/拒绝数量，GET /bigmodel/api/audit/stats","StatsCard.tsx","0.1","4/23","4/23，统计正确，待开发"]
["P2，权限管理系统，AUTH-001，用户权限获取，获取当前用户权限列表，GET /api/auth/permissions，权限逻辑，0.3","4/24","4/24，权限数据正确，待开发"]
["P2，权限管理系统，AUTH-002，角色管理对接，获取用户角色信息，GET /api/auth/roles，角色逻辑，0.2","4/24","4/24，角色数据正确，待开发"]
["P2，权限管理系统，AUTH-003，按钮权限控制，根据权限显示/隐藏功能按钮，-","权限指令，0.3","4/24","4/24，权限控制生效，待开发"]
["P2，权限管理系统，AUTH-004，页面访问控制，无权限页面重定向，-","路由守卫，0.2","4/24","4/24，路由拦截正确，待开发"]

{"sheet":"模块概览","index":1,"n_rows":43,"n_cols":7,"rows_kept":43,"cut":false,"hidden":false,"merged":[[0,0,0,6]]}
["模块概览"]
[]
["优先级","模块名称","总工期","开始日期","结束日期","任务数","状态"]
["P0，应用广场，APP-001，应用列表展示，展示应用卡片列表，支持分页，GET /bigmodel/api/getApplicationList","AppPlazaList.tsx","0天",null,null,"1个","待开发"]
["P0，应用广场，APP-002，应用卡片组件，应用卡片 UI 包含图标名称描述标签等，-","AppCard.tsx","0天",null,null,"1个","待开发"]
["P0，应用广场，APP-003，筛选功能，支持按分类状态关键词筛选，POST /bigmodel/api/getApplicationList (params)","FilterBar.tsx|FilterDrawer.tsx","0天",null,null,"1个","待开发"]
["P0，应用广场，APP-004，排序功能，综合排序最新上线高频率调用，前端排序，排序按钮组件，0.5","4/8","0天",null,null,"1个","待开发"]
["P0，应用广场，APP-005，应用详情，点击卡片查看详情，GET /bigmodel/api/selectApplication/:id","AppDetailModal.tsx","0天",null,null,"1个","待开发"]
["P0，应用广场，APP-006，立即体验，跳转至智能问答界面，-","跳转逻辑，0.25","0天",null,null,"1个","待开发"]
["P0，应用广场，APP-007","API 调用入口，查看 API 文档获取调用凭证，GET /bigmodel/api/getAppApiKey","0天",null,null,"1个","待开发"]
["P0，应用广场，APP-008，联调测试，与后端联调验证数据交互，全部应用相关接口，-","0.5","0天",null,null,"1个","待开发"]
["P0","API 接口，API-001","0天",null,null,"1个","待开发"]
["P0","API 接口，API-002，创建 API Key，弹窗创建新的 API Key","0天",null,null,"1个","待开发"]
["P0","API 接口，API-003，删除 API Key，删除 API Key 确认弹窗，DELETE /bigmodel/api/apiKey/delete，确认弹窗，0.25","0天",null,null,"1个","待开发"]
["P0","API 接口，API-004","0天",null,null,"1个","待开发"]
["P0","API 接口，API-005，接口文档页面，展示 RAG 调用接口文档，-","0天",null,null,"1个","待开发"]
["P0，知识库，KB-001，知识库列表，展示知识库列表支持分页，POST /bigmodel/api/knowledgeList","KnowledgeLibList.tsx","0天",null,null,"1个","待开发"]
["P0，知识库，KB-002，创建知识库，弹窗创建知识库，POST /bigmodel/api/createKnowledge","InfoModal.tsx","0天",null,null,"1个","待开发"]
["P0，知识库，KB-003，编辑知识库，修改知识库信息，PUT /bigmodel/api/updateKnowledge","InfoModal.tsx","0天",null,null,"1个","待开发"]
["P0，知识库，KB-004，删除知识库，删除知识库含确认，DELETE /bigmodel/api/delKnowledge，确认弹窗，0.25","4/15","0天",null,null,"1个","待开发"]
["P0，知识库，KB-005，知识库详情，进入知识库详情页，GET /bigmodel/api/detailKnowledge/:id","KnowledgeDetail.tsx","0天",null,null,"1个","待开发"]
["P0，知识库，KB-006，文档管理，文档列表上传删除，POST /bigmodel/api/documentList 等，DocumentList.tsx","0.5","0天",null,null,"1个","待开发"]
["P0，知识库，KB-007，切片管理，查看和编辑文档切片，POST /bigmodel/api/getSliceList","SliceList.tsx","0天",null,null,"1个","待开发"]
["P0，知识库，KB-008，修订工具，切片修订历史与对比，GET /deepseek/revise/pageList","RevisionTool.tsx","0天",null,null,"1个","待开发"]
["P0，知识库，KB-009，联调测试，与后端联调知识库接口，全部知识库接口，-","0.5","0天",null,null,"1个","待开发"]
["P1，我创建的应用，MYAPP-001，我的应用列表，展示当前用户创建的应用，GET /bigmodel/api/myApplications","MyApplicationsList.tsx","0天",null,null,"1个","待开发"]
["P1，我创建的应用，MYAPP-002，应用状态筛选，全部/已上线/已下线/审核中，前端筛选，Tabs 组件，0.25","4/17","0天",null,null,"1个","待开发"]
["P1，我创建的应用，MYAPP-003，编辑应用，修改应用配置，PUT /bigmodel/api/updateApplication/:id","AppEditForm.tsx","0天",null,null,"1个","待开发"]
["P1，我创建的应用，MYAPP-004，应用数据统计，调用次数用户数等统计，GET /bigmodel/api/app/stats","StatsPanel.tsx","0天",null,null,"1个","待开发"]
["P1，我创建的应用，MYAPP-005，应用下线/上线，切换应用状态，PUT /bigmodel/api/updateApplication/status，状态切换按钮，0.25","4/18","0天",null,null,"1个","待开发"]
["P1，智能问答系统，CHAT-001，应用跳转问答，从应用广场跳转到问答系统，-","跳转逻辑，0.25","0天",null,null,"1个","待开发"]
["P1，智能问答系统，CHAT-002，问答接口对接，RAG 检索 + 大模型回答，POST /bigmodel/api/chat/stream","ChatInterface.tsx","0天",null,null,"1个","待开发"]
["P1，智能问答系统，CHAT-003，历史记录同步，获取和展示聊天历史，POST /bigmodel/api/chatHistory/list","HistoryList.tsx","0天",null,null,"1个","待开发"]
["P1，智能问答系统，CHAT-004，跨系统通信，两个系统间用户态同步，-","通信逻辑，0.25","0天",null,null,"1个","待开发"]
["P2，应用审核，AUDIT-001，审核列表，展示待审核/已通过/已拒绝应用，GET /bigmodel/api/audit/list","AuditList.tsx","0天",null,null,"1个","待开发"]
["P2，应用审核，AUDIT-002，审核通过，审核通过操作，POST /bigmodel/api/audit/approve，审核弹窗，0.2","4/23","0天",null,null,"1个","待开发"]
["P2，应用审核，AUDIT-003，审核拒绝，审核拒绝操作，POST /bigmodel/api/audit/reject，审核弹窗，0.2","4/23","0天",null,null,"1个","待开发"]
["P2，应用审核，AUDIT-004，应用详情预览，查看应用详情及知识库，GET /bigmodel/api/audit/detail/:id","AuditDetailDrawer.tsx","0天",null,null,"1个","待开发"]
["P2，应用审核，AUDIT-005，审核统计，待审核/通过/拒绝数量，GET /bigmodel/api/audit/stats","StatsCard.tsx","0天",null,null,"1个","待开发"]
["P2，权限管理系统，AUTH-001，用户权限获取，获取当前用户权限列表，GET /api/auth/permissions，权限逻辑，0.3","4/24","0天",null,null,"1个","待开发"]
["P2，权限管理系统，AUTH-002，角色管理对接，获取用户角色信息，GET /api/auth/roles，角色逻辑，0.2","4/24","0天",null,null,"1个","待开发"]
["P2，权限管理系统，AUTH-003，按钮权限控制，根据权限显示/隐藏功能按钮，-","权限指令，0.3","0天",null,null,"1个","待开发"]
["P2，权限管理系统，AUTH-004，页面访问控制，无权限页面重定向，-","路由守卫，0.2","0天",null,null,"1个","待开发"]

{"sheet":"API 接口清单","index":2,"n_rows":8,"n_cols":5,"rows_kept":8,"cut":false,"hidden":false,"merged":[[0,0,0,4]]}
["API 接口清单"]
[]
["接口名称","请求方式","接口地址","所属模块","状态"]
["UI","UI","UI","AppCard.tsx","待联调"]
["4/9，弹窗展示","4/9，弹窗展示","4/9，弹窗展示","API 调用入口，查看 API 文档获取调用凭证，GET /bigmodel/api/getAppApiKey","待联调"]
["4/10","4/10","4/10","API 接口，API-001","待联调"]
["4/11，图表渲染正确，待开发","4/11，图表渲染正确，待开发","4/11，图表渲染正确，待开发","API 接口，API-004","待联调"]
["4/11，文档页面完成，待开发","4/11，文档页面完成，待开发","4/11，文档页面完成，待开发","API 接口，API-005，接口文档页面，展示 RAG 调用接口文档，-","待联调"]

{"sheet":"里程碑节点","index":3,"n_rows":9,"n_cols":4,"rows_kept":9,"cut":false,"hidden":false,"merged":[[0,0,0,3]]}
["里程碑节点"]
[]
["里程碑","日期","交付内容","状态"]
["M1 - 应用广场完成","4/9","应用列表、筛选、排序、详情功能完成","待完成"]
["M2 - API 接口完成","4/11","API Key 管理、调用统计完成","待完成"]
["M3 - 知识库完成","4/16","知识库 CRUD、文档管理、切片管理完成","待完成"]
["M4 - 我创建的应用完成","4/18","我的应用列表、编辑、统计完成","待完成"]
["M5 - 智能问答联调完成","4/22","RAG 对话接口、历史记录完成","待完成"]
["M6 - 全部完成","4/24","所有模块联调完成，准备上线","待完成"]